## Control Risk Matrix
Process Area | Risk Area | Risk Description | Control Objective | Control Activity | Control Type | Frequency | Owner | Evidence Required | System/Data Dependency | Related Requirement ID | Related UAT Case | Residual Risk / Implementation Note
Payroll Controls | Starter and leaver control gaps | Payroll Controls may experience starter and leaver control gaps if ownership, data, controls, and evidence are not defined before build. | Reduce risk from starter and leaver control gaps through clear ownership, evidence, and review criteria. | Starter, leaver, salary, deduction, and bank detail changes require approval before payroll processing. | Preventive | Each payroll cycle | Payroll Controls Owner | Store payroll master change request, approval, processing, and effective date history. | Sage Payroll and Xero Finance data, required fields, owner status, and evidence references must be available for review. | FR-01 | UAT-01 | HR and payroll ownership of master data changes must be agreed.
Payroll Controls | Payroll change approval delays | Payroll Controls may experience payroll change approval delays if ownership, data, controls, and evidence are not defined before build. | Reduce risk from payroll change approval delays through clear ownership, evidence, and review criteria. | Payroll input files require preparer and reviewer sign-off before calculation. | Detective | Each payroll cycle | Payroll Controls Owner | Record payroll input file version, preparer, reviewer, approval, and cutoff timestamp. | Sage Payroll and Xero Finance data, required fields, owner status, and evidence references must be available for review. | FR-02 | UAT-02 | Payroll cutoff rules and approval thresholds require policy sign-off.
Payroll Controls | Manual payroll input checks | Payroll Controls may experience manual payroll input checks if ownership, data, controls, and evidence are not defined before build. | Reduce risk from manual payroll input checks through clear ownership, evidence, and review criteria. | Payroll exceptions over threshold require investigation and approval. | Corrective | Each payroll cycle | Payroll Controls Owner | Preserve exception review notes and approval decisions. | Sage Payroll and Xero Finance data, required fields, owner status, and evidence references must be available for review. | FR-03 | UAT-03 | Sensitive payroll access roles must be configured carefully.
Payroll Controls | Starter and leaver control gaps | Payroll Controls may experience starter and leaver control gaps if ownership, data, controls, and evidence are not defined before build. | Reduce risk from starter and leaver control gaps through clear ownership, evidence, and review criteria. | Payroll register must reconcile to GL control accounts and payment file totals. | Manual | Each payroll cycle | Payroll Controls Owner | Track payroll reconciliation owner/status history by period. | Sage Payroll and Xero Finance data, required fields, owner status, and evidence references must be available for review. | FR-04 | UAT-04 | GL account mapping must be validated before reconciliation testing.
Payroll Controls | Payroll change approval delays | Payroll Controls may experience payroll change approval delays if ownership, data, controls, and evidence are not defined before build. | Reduce risk from payroll change approval delays through clear ownership, evidence, and review criteria. | Payroll payment file release requires finance approval. | Automated | Each payroll cycle | Payroll Controls Owner | Keep payment file approval evidence with approver, date, amount, and bank file reference. | Sage Payroll and Xero Finance data, required fields, owner status, and evidence references must be available for review. | FR-05 | UAT-05 | Historic payroll exception categories may need standardisation before rollout.